## Sprint 1 - Recruitment Portal
Module | Task | Description | Estimated Hours | Owner | Status
Auth | OAuth2 Integration | Implement Google and Microsoft SSO login | 8 | Fazil | In Progress
Auth | JWT Token Rotation | Add refresh token rotation middleware | 6 | Fazil | Completed
Candidate | Resume Parser | Extract contact and skill data from PDF | 12 | Reka | In Progress
Candidate | Profile Search | Build multi-filter candidate search UI | 10 | Reka | To Do

## Sprint 2 - iWork
Module | Task | Description | Estimated Hours | Owner | Status
Workflow | Approval Engine | Implement multi-level leave approval | 16 | Fazil | To Do
Analytics | Dashboard Metrics | Generate department velocity charts | 8 | Reka | In Progress
Reports | Audit Export | Export compliance logs to encrypted spreadsheet | 4 | Fazil | To Do